## Sheet1
STATIONS | Owner | Ops | Kiosk | Vending & News Boxes | Benches | Trash Receptacle | Bike Rack | TVM | Clock | Signs | Parking | Platforms, Stairs, Ramps | Canopy | Paths | Railing | Fence | Lighting | Station Building | Shelters | Litter | ADA | General
State Street | CDOT | CDOT | - | -- | -- | -- | Install, if warranted | -- | Add clock to platform | Trailblaze; Entrance; review signage | No parking | Minor platform repairs | Touch up paint | Ped Bridge Good | Need paint; Extend rail at platform ends | Good | Evaluate | None | Enclosed ped bridge | Some graffitti | Compliant, some code issues | Nice station
New Haven | CDOT | NHPA | - | Remove from Platforms | Add to platforms | Add | Install, if warranted | -- | Add clocks to platforms | Trailblaze; Entrance; review signage | Expand garage | Minor platform repairs, Need platform end ramp tactile | Paint, Drainage repairs | Review track crossing, tunnel repairs | Fix connections | Fix platform end railing | Evaluate, broken canopy lights, corroded bases | See code review | Enclosed stairways | Clean | Compliant, some code issues | Capital improvements scheduled
Milford | CDOT | MTD | Add 2 | Remove from Platforms | -- | -- | Install, if warranted | Add EB TVM | Add clocks to platforms | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs; Catenary | -- | Review after construction | New | Fix broken fence, replace EB gate | Evaluate & update as required | Rehabilitated | None | Assess after construction | Compliant, some code issues | Assess after construction; Historic buildings
Stratford | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | -- | Add EB TVM | Add clocks to platforms | Trailblaze; Entrance; review signage | Build new garage | Platform repairs; Tactile edge; Extend 500 ft (x2); Catenary | Add canopy: 400 ft EB & 200 ft EB | Add walk/rail along track; Replace bit walks | Replace old aluminum railing | Replace weathered CL fence & railiing | Post-mount lights on paths; Evaluate & update | Exterior paint, Sill damage | Need repairs & glazing; Replace | Butts behind platforms | Non-compliant | City has improve entrances; Historic buildings
Bridgeport | CITY | CDOT | - | Remove from Platforms | Replace Alum Benches | Add & Replace | -- | -- | Add clocks to platforms | Trailblaze; Entrance; review signage | See code review; Information Signs | Platform repairs; Fix EB holes; Extend 170 ft; Catenary | Clean & paint; New paint scheme | Maintain during construction, EB Walk? | Replace old aluminum railing | Replace weathered CL fence | Post-mount lights on paths; Evaluate & update | See code review | None | Under/behind platforms | Key Sta., Need VMS, FTA Review | City plans new Trans. Center, Construction updates needed
Fairfield | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Install, if warranted | Add EB TVM | Replace WB; Add EB clock | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs; Tactile edge; Catenary; Extend 350 ft | Paint; Replace WB; Add 200 ft EB | Add walk/rail along track; Replace bit walks | Replace old aluminum railing | Replace CL fence; Add walk | Post-mount lights on paths; Evaluate & update | Closed on day of visit | Need repairs & glazing; Replace | -- | Non-compliant; Add Ped bridge | Key station reassigned to Fairfield Metro; Historic buildings
Southport | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Replace EB rack | Add EB TVM | Add clocks to platforms | Trailblaze; Entrance; review signage | Parking Information Sign EB side | Platform repairs; Tactile edge; Catenary; Extend 500 ft | Paint; Replace WB; Add 200 ft EB | Fix or eliminate EB Stair; Replace bit walks | Replace old aluminum railing | Replace weathered CL fence & railing | Post-mount lights on paths; Evaluate & update | Bathroom floor & stall | Add EB shelter | Behind WB platform | Non-compliant; Provide ADA route | Restored Historic building
Green's Farms | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Replace | Add EB TVM | Add clocks to platforms | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs;Tactile edge; Catenary; Extend 350 ft | Paint; Replace WB; Add 200 ft EB | EB platform protrudes; Replace all walks | Replace old aluminum railing | Replace weathered CL fence & railing | Post-mount lights on paths; Evaluate & update | Closed on day of visit | Needs glazing; Replace | Graffiti under platform | Non-compliant | Close dead end EB walk; Restored station building
Westport | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Install, if warranted | -- | Replace WB; Add EB clock | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs; Catenary; Ramp tactile strips | Paint; Gutter repairs; Replace | Add walk/rail along track; Replace bit walks | Repair/Replace old aluminum railing | Replace weathered CL fence & railing | Replace platform fixtures; Post-mount lights on paths | Nicely Restored | Need repairs & glazing; Replace | Bagged trash under stairs | Compliant; VMS signs | Saga Bridge replacement begins 2009; Restored station building
East Norwalk | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Install, if warranted | Add EB TVM | Add clocks to platforms | Trailblaze; Entrance; review signage | Info signs; Add walk to EB parking | Platform repairs; Tactile edge; Catenary; Extend 500 ft | Paint; Replace WB; Add 200 ft EB | Replace bit walks and railing; | Replace steel & aluminum railing | Replace weathered CL fence & railing | Post-mount lights on paths; Evaluate & update | Closed on day of visit | Good | Clean | Non-compliant | Off-set platforms; New station building
South Norwalk | CITY | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Replace | -- | Add clocks | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs; Catenary | Extend canopies 200 ft each side | Trim weeds; Improve Monroe St. EB driveway | Replace aluminum railing | Replace weathered CL fence & railing | Post-mount lights on paths; Evaluate & update | Code & rest room issues | Good | Track level litter | Compliant; Code issues; VMS sign | Onging Catenary B construction
Rowayton | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Replace | Add EB TVM | Add clocks to platforms | Trailblaze; Entrance; review signage | -- | Platform repairs; Tactile edge; Catenary; Extend 350 ft | Drainage repairs; Add 200 ft EB | Add walk/rail along track; Replace bit walks | Replace aluminum & cast iron railing | Replace CL fence & cast iron railing | Replace platform fixtures; Post-mount lights on paths | Closed on day of visit | Good | Clean | Non-compliant | Onging Catenary B construction
Darien | CDOT | CITY | Add 2 | Remove from Platforms | Fix broken EB bench | Add; move recycle bins | -- | Add EB TVM | Add clocks to platforms | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs; Catenary; Rusted stairs | -- | New; Some concrete cracks & spall | Replace old aluminum railing | Inspect after Cat B construction | Platform lighting being replaced | Touch up Exterior trim | None | Clean; Recycle close to TVM | Compliant; Code issues; VMS sign | Catenary B construction; Recently rehabiltated station building
Noroton Heights | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Install, if warranted | Add EB TVM | Replace WB; Add EB clock | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs; Tactile edge; Catenary | Paint; Replace WB; Add 200 ft EB | Add walk/rail along track; Replace bit walks | Replace old aluminum railing | Replace weathered CL fence & railing | Replace platform fixtures; Post-mount lights on paths | Expand rest room | Need repairs & glazing; Replace | Track level litter | Non-compliant | Clean & paint ped bridge; ADA upgrade; Catenary B construction
Stamford | CDOT | CDOT | Update Tunnel | -- | Replace Alum Benches | Add & Replace | Install, if warranted | -- | Add clocks to platforms | Trailblaze; Entrance; review signage | Info Signs; Repair/ Replace Garage | Bird droppings; Stair nosings | Resolve bird issue | New | New | New | New | Rehabilitated; Floor curling | New | Clean | Compliant; VMS signs needed | Major repairs to and/or replacement of 1985 garage
Old Greenwich | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | -- | Add EB TVM | Replace WB; Add EB clock | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs; Tactile edge; Catenary; Extend 350 ft | Paint; Replace WB; Add 200 ft EB | EB platform protrudes; Replace all bit walks | Replace old aluminum railing | Replace weathered CL fence & railing | Post-mount lights on paths; Evaluate & update | Closed on day of visit | Need repairs & glazing; Replace | Some litter | Non-compliant | Historic building
Riverside | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Install, if warranted | Add EB TVM | Replace WB; Add EB clock | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs; Tactile edge; Catenary; Extend 350 ft | Paint; Drainage; Replace WB; Add EB | Add walk/rail along track; Replace bit walks | Replace old aluminum railing | Replace weathered CL fence & railing | Post-mount lights on paths; Evaluate & update | Closed on day of visit | Need repairs & glazing; Replace | Some litter | Non-compliant | Historic building
Cos Cob | CDOT | CITY | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Install, if warranted | Add EB TVM | Replace WB; Add EB clock | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs; Tactile edge; Catenary; Extend 350 ft | Paint; Drainage; Replace WB; Add EB | Add walk/rail along track; Replace bit walks | Replace old aluminum railing | Replace weathered CL fence & railing | Post-mount lights on paths; Evaluate & update | Closed on day of visit | Need repairs & glazing; Replace | Clean | Non-compliant | Historic building
Greenwich | Private | Private | Add 2 | Remove from Platforms | Replace Alum Benches | Add & Replace | Install, if warranted | -- | -- | Trailblaze; Entrance; review signage | Parking Information Signs | Platform repairs; Catenary; Existing 8-Car Platform | Paint; Drainage repairs | Some concrete cracks; Dead end areas | Replace old aluminum railing | Replace weathered CL fence & railing | Evaluate & update as required | Clean | New | Clean | Compliant; Code issues; VMS sign | New ped bridge
New Canaan | CDOT | CITY | Add 1 | -- | Add Benches | Replace | -- | -- | Add clock | Trailblaze; Entrance; review signage | Parking Information Signs | Bird droppings | Repair roof damage | Replace bit walks; | -- | -- | Evaluate & update as required | Clean | None | Track level trash | Compliant; Some code issues | Recently rehabilitated historic building
Talmadge Hill | CDOT | CITY | Add 1 | Remove from Platforms | Replace Alum Benches | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Parking Information Signs | Minor platform repairs; Tactile edge; Replace metal grating | Add 100 ft canopy | Replace bit walks; add railing; add sidewalk | Replace old aluminum railing | Add fence on east side; Along Merritt | Post-mount lights on paths; Evaluate & update | None | Need repairs & glazing; Replace | Track level trash | Non-compliant | Station cannot be expanded w/o major construction/relocation
Springdale | CDOT | CDOT | Add 1 | Remove from Platforms | Replace Alum Benches | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Parking Information Signs | Minor platform repairs; Tactile edge | Add 100 ft canopy | Add walk/rail along track; Walk behind platform | Replace old aluminum railing | Replace weathered CL fence & railing | Post-mount lights on paths; Evaluate & update | None | Need repairs & glazing; Replace | Track level trash | Non-compliant | Replace Hope Street bus shelter and improve path to platform
Glenbrook | CDOT | CDOT | Add 1 | Remove from Platforms | Replace Alum Benches | Add & Replace | -- | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Parking Information Signs | Minor platform repairs; Tactile edge; Platform end railing | Add 100 ft canopy | Add walk/rail along track; Replace bit walks | Replace old aluminum railing | Replace weathered CL fence & railing | Post-mount lights on paths; Evaluate & update | None | Need repairs & glazing; Replace | Track level trash | Non-compliant | Considered relocating City Traffic Department from parking lot
Danbury | CDOT | CITY | Add 1 | -- | Add benches | Add & Replace | Install, if warranted | -- | Add clock | Trailblaze; Entrance; review signage | Parking Information Signs | Minor platform repairs | -- | Trim vegetation | -- | Replace weathered & broken CL fence | Post-mount lights on paths; Evaluate & update | Clean; Post station hours | None | Track level trash | Compliant; Some code issues | Maintain landscaping; Protect A/C compressors
Bethel | CDOT | CITY | Add 1 | -- | Add benches | Add & Replace | Replace | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Info Signs; Seal pvmt cracks; Repaint lines | Minor platform repairs; Bird droppings | -- | Some concrete cracks | Replace old aluminum railing | Paint touch-up needed | Post-mount lights on paths; Evaluate & update | Clean; Post station hours | None | Empty trash often | ADA accessible; Code issues | Nice station with park-like atmosphere
West Redding | CDOT | CITY | Add 1 | -- | -- | Add | Install, if warranted | Add TVM, if warranted | Add clock | Move entrance sign; review all signage | -- | Extend, if ridership warranted | Refinish wood surfaces | Maintain landscaping | -- | Replace weathered CL fence | Evaluate & update as required | None | Refinish wood surfaces | Clean | ADA accessible; Code issues | Nice rural station
Branchville | CDOT | CITY | Add 1 | -- | Replace Alum Benches | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Info signs; Repair pvmt; Trim vegetation | Minor platform repairs; Tactile edge; Trim vegetation | Clean & paint; Drainage repairs | Replace footbridge over river; Trim vegetation | Replace old aluminum railing | -- | Post lights south path; trim trees; Evaluate & update | Gutter; Public rest room | Provide if no waiting room | Clean | ADA accessible; Code issues | Need payphone; Inspect entrance bridges; Historic building
Cannondale | CDOT | City/ CDOT | Add 1 | -- | Replace Alum Benches | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Info signs; Seal pvmt cracks; Repaint lines | Minor platform repairs; Tactile edge; Bird droppings, Extend | Clean & paint; Remove bird nests | Add walk/railing along track; Replace bit/gravel | Replace old aluminum railing | Replace weathered CL fence | Post-mount lights on paths; Evaluate & update | Add rest and waiting rooms | Provide if no waiting room | Clean | ADA accessible; Code issues | Rest rooms being built; Historic building
Wilton | CDOT | City/ CDOT | Add 1 | Remove from platform ramp | Add bench | Add & Replace | Install, if warranted | -- | Add clock | Trailblaze; Entrance; review signage | Parking Information Signs | Minor platform repairs; Tactile edge | -- | Add walk/railing along track; Replace bit paths | Replace old aluminum railing | Replace weathered CL fence | Post-mount lights on paths; Evaluate & update | Add station hour sign | None | Some litter | ADA accessible; Code issues | Monitor ongoing Route 7 construction; Historic building
Merritt 7 | CDOT | CDOT | Add 1 | -- | -- | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Parking Information Signs | None, Add high-level platform | Add canopy with new platform | Add walk/railing along track; Replace bit paths | Add railing along track | Replace weathered CL fence | Post-mount lights on paths; Evaluate & update | None | Need repairs & glazing; Replace | Clean | Non-compliant | Only low-level platform on Danbury Branch
Waterbury | CDOT | CDOT | -- | -- | Replace Alum Benches | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock; Fix tower clock | Trailblaze; Entrance; review signage | Parking Information Signs; Fix entrance | Minor platform repairs | -- | Define walks to platform | Replace old aluminum railing | Replace weathered CL fence, Add | Post-mount lights on paths; Evaluate & update | None | Good | Clean | Compliant; Code issues; VMS sign | Only high-level platform on Waterbury Branch
Naugatuck | CDOT | CDOT | Add 1 | -- | -- | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Parking Information Signs | Replace mid-level with high-level platform | Add canopy with new platform | Add walk/railing along track; Replace bit paths | Replace steel pipe railing | Add fence/railing along track | Post-mount lights on paths; Evaluate & update | None | Need repairs & glazing; Replace | Clean | Non-compliant | Historic building being restored by City
Beacon Falls | CDOT | CDOT | Add 1 | -- | -- | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Parking Information Signs; Fix entrance | Replace mid-level with high-level platform | Add canopy with new platform | Add walk/railing along track; Replace bit paths | Replace steel pipe railing | Add fence/railing along track | Post-mount lights on paths; Evaluate & update | None | Need repairs & glazing; Replace | Clean | Non-compliant | Remote location
Seymour | CDOT | CDOT | Add 1 | -- | Add benches | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Info Signs; Directions to daily parking areas | Repair wood boxes; Add high-level platform | Add canopy with new platform | Add walk/railing along track; Replace bit paths | -- | Add fence/railing along track | Post-mount lights on paths; Evaluate & update | None | Brick shelter; Odor | Clean | Non-compliant | Downtown location
Ansonia | CDOT | CDOT | Add 1 | -- | Replace Bench | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Info signs; Eliminate parking area | Repair wood box; Add high-level platform & canopy | Scrape & paint; Preserve; Add new | Add walk/railing along track; Replace bit paths | -- | Add fence/railing along track | Post-mount lights on paths; Evaluate & update | None | Good | Clean | Non-compliant | Nice retro train stop; Consider small trees on west side of tracks
Derby/ Shelton | CDOT | CDOT | Add 1 | -- | Add benches | Add & Replace | Install, if warranted | Add TVM, if warranted | Add clock | Trailblaze; Entrance; review signage | Parking Information Signs | Repair wood box; Add high-level platform/canopy to north | Scrape & paint; Add new with platform | Add walk/railing along track; Replace bit paths | -- | Add fence/railing along track | Post-mount lights on paths; Evaluate & update | Power wash brick | Need repairs & glazing; Replace | Clean | Non-compliant | Valley Transit next door; Historic buildings