## Pre-FDP_template
SUMMARY OF ESTIMATED PROJECT COST
N/A Fields
Required Fields
Project Number: |  |  |  |  | Current Schedule
Description: |  |  |  | PE-FD
Lead Design Unit: |  | Estimate Date: |  | FDP
Project Manager: |  | Current Estimate: |  | DCD
Estimated By: |  | Checked By: |  | ADV
COST SUMMARY
Phase | Activity |  | Cost to Project 1 | Start year | Duration (years)
PE | PRELIMINARY DESIGN
PE | MUNICIPAL PROJECTS STATE COST
PE | MUNICIPAL PROJECTS TOWN COST
PE | FINAL DESIGN
RW | RIGHT OF WAY
CN | CONSTRUCTION CONTRACT
CN | UTILITIES 2
CN | RAILROAD
CN | INCIDENTALS (CENG)
CN | CONTINGENCY 3
CN | STATE POLICE
CN | OTHER (Specify)
CN | OTHER (Specify)
| Total Estimated Cost of Design (PE) Phase |  |  | 0
| Total Estimated Cost of R/W Phase |  |  | 0
| Total Estimates Cost of Construction Phase |  |  | 0
| TOTAL PROJECT COST |  |  | 0
# | Notes | Phase | Description
1 | All actual or estimated costs in year of expenditure, Inflation adjusted | PPI | Proposed Project Information
2 | Cost to State project based on location (highway classification) and utility owner | PE-PD | Preliminary Engineering - Preliminary Design
3 | Contingency based on project development phase as indicated by: | PE-FD | Preliminary Engineering - Final Design
| CTDOT Cost Estimating Guidelines | DESIGN | Estimate submitted at FDP

## Pre-FDP_example
SUMMARY OF ESTIMATED PROJECT COST
N/A Fields
Required Fields
Project Number: | 123-456 |  |  |  | Current Schedule
Description: | Sample Project |  |  | PE-FD
Lead Design Unit: | Highway Design | Estimate Date: | 2019-02-02 | FDP
Project Manager: | John Smith | Current Estimate: |  | DCD
Estimated By: | John Doe | Checked By: | Jane Checker | ADV
COST SUMMARY
Phase | Activity |  | Cost to Project 1 | Start year | Duration (years)
PE | PRELIMINARY DESIGN |  | 108256 | 2018 | 1
PE | MUNICIPAL PROJECTS STATE COST |  | 75000 | 2019 | 1
PE | MUNICIPAL PROJECTS TOWN COST |  | 325000 | 2019
PE | FINAL DESIGN |  | 325000 | 2019 | 2
RW | RIGHT OF WAY |  | 150000 | 2020 | 2
CN | CONSTRUCTION CONTRACT |  | 4760000 | 2021 | 3
CN | UTILITIES 2 |  | 316000 | 2021 | 2
CN | RAILROAD |  | 128000 | 2021 | 1
CN | INCIDENTALS (CENG) |  | 1190000 | 2021 | 3
CN | CONTINGENCY 3 |  | 952000 | 2021
CN | STATE POLICE |  | 187000 | 2021
CN | OTHER (Specify)
CN | OTHER (Specify)
| Total Estimated (State) Cost of Design (PE) Phase |  |  | 833256
| Total Estimated (State) Cost of R/W Phase |  |  | 150000
| Total Estimates (State) Cost of Construction Phase |  |  | 7533000
| TOTAL PROJECT COST |  |  | 8516256
# | Notes | Phase | Description
1 | All actual or estimated costs in year of expenditure, Inflation adjusted | PPI | Proposed Project Information
2 | Cost to State project based on location (highway classification) and utility owner | PE-PD | Preliminary Engineering - Preliminary Design
3 | Contingency based on project development phase as indicated by: | PE-FD | Preliminary Engineering - Final Design
| CTDOT Cost Estimating Guidelines | DESIGN | Estimate submitted at FDP

## FDP_single_template
FINAL DESIGN PLAN CONSTRUCTION COST ESTIMATE - SINGLE PROJECT
Required Fields
Project Number:
Description:
Lead Design Unit:
Project Manager: |  | Estimate Date:
Estimated By: |  | Checked By:
Construction Contract
Non-contract Items
Incidentals
Contingency
Utilities (State Share, Construction)
Railroad Force Account
State Police
Other (specify)
| TOTAL |  | 0

## FDP_single_example
FINAL DESIGN PLAN CONSTRUCTION COST ESTIMATE - SINGLE PROJECT
Required Fields
Project Number: | 1234-5678
Description: | Sample Project
Lead Design Unit: | Highway Design
Project Manager: | John Smith | Estimate Date: | 2019-02-02
Estimated By: | John Doe | Checked By: | Jane Checker
Construction Contract |  |  | 25785491.5
Non-contract Items
| Incidentals |  | 3867823.725
| Contingency |  | 2578549.15
| Utilities (State Share, Construction) |  | 87650
| Railroad Force Account |  | 143250
| State Police |  | 189000
Other (specify)
| TOTAL |  | 32651764.375

## FDP_combination_template
FINAL DESIGN PLAN CONSTRUCTION COST ESTIMATE - MULTI-PROJECT CONTRACT
Required Fields |  |  | Project 1 | Project 2 | Contract
Contract Number: |  | Project Number:
Description:
Lead Design Unit:
Project Manager: |  | Estimate Date:
Estimated By: |  | Checked By:
|  |  | Project 1 | Project 2 | Contract
Construction Contract
Non-contract Items
Incidentals
Contingency
Utilities (State Share, Construction)
Railroad Force Account
State Police
Other (specify)
TOTAL

## FDP_combination_example
FINAL DESIGN PLAN CONSTRUCTION COST ESTIMATE - MULTI-PROJECT CONTRACT
Required Fields |  |  | Project 1 | Project 2 | Contract
Contract Number: | 123-456 | Project Number: | 123-456 | 123-456 | 123-456
Description: | Sample Project
Lead Design Unit: | Higways
Project Manager: | Jane Simmons | Estimate Date: | 2019-08-12
Estimated By: | John Lightman | Checked By: | John Checker
|  |  | Project 1 | Project 2 | Contract
Construction Contract |  |  | 2911449.92 | 926674.26 | 3838124.18
Non-contract Items
| Incidentals |  | 1019007.47 | 324335.99 | 1343343.46
| Contingency |  | 291144.99 | 92667.43 | 383812.42
| Utilities (State Share, Construction) |  |  | 407000 | 407000
| Railroad Force Account |  |  | 180000 | 180000
| State Police |  | 85000 |  | 85000
| Other (specify) |  |  |  | 0
0
| TOTAL |  | 4306602.38 | 1930677.68 | 6237280.06

## Lists
PHASE
PPI
PE-PD
PE-FD
DESIGN