## Sheet1
Work Plan - DRAFT
Cross Agency Population Results Subcommittee
| Activity | Description | Outcome | Timeline
1 | Identify additional workgroup members to work group co-chairs at DCF, SDE, DMHAS, DPH, DOC, DDS, and DSS | In collaboration with Agency Commissioners, identify key personnel within each Human Services Agency to participate in workgroup | Representation from each Human Services Agency | 2012-01-01
2 | Inventory existing Population Results Statements from Human Services Agencies | In coordination with the Appropriations Committee of the General Assembly, create a comprehensive inventory of Population Results Statements | Joint-inventory of Population Results Statements | 2012-01-15
3 | Provide RBA training for state agency workgroup members | Assist work group members to understand RBA framework and application; Training dates - 01/30/2012 and 02/09/2012 | Work group members have a working understanding of RBA framework | 2012-02-15
4 | Develop additional Population Results Statement | Utilizing workgroup members from Human Services Agencies, develop additional Population Results Statements | Complete listing of Population Results Statements | 2012-03-01
5 | Identify Indicators for each Population Results Statement | Develop and evaluate Indicators utilizing RBA framework | Population-level Indicators for each Results Statement | 2012-04-01
6 | Identify data sources for each Indicator | Utilizing CT resources when possible, identify sources that can provide baseline data for each indicator | Data sources for each Indicator | 2012-04-01
7 | Create Data Development Agenda for Indicators lacking a data source | For data that is not available, create a data development agenda to guide future data sources | Data development agenda | 2012-04-01
8 | Develop and implement process for obtaining input from specific state agency target populations and nonprofits to test the relevance and clarity of population results statements. |  | Feedback and refinement of population results statements | 2012-05-01
9 | Assemble final report for submission to Human Services Cabinet |  | Final Report | 2012-06-01